## Project
Review check list for Project
Phases to be verified | Check If / For
Software Project Agreement and Authorisation | 1. Whether project authorisation issued
2. Whether Userneed document prepared
3. Whether project kick off meeting conducted
4. PM, PL, QA Member identified?
5. The project code convention should be “<Customer Short Code><Product Short Name>_<Product Version Number>”
6. The naming convention for all SCIs and document work products should be “<Project Code>_<Document Short Name>”
7. Document ID format should be ICS/<Project Code>/<DocumentAbbreviation>
Project planning | 1. Whether FP, PP reviewed and approved
2. Whether resource plan prepared
3. When is the project start date and end date
4. Whether the PP contain lifecycle phases description?
5. Whether the PP contain effort estimation and Schedule for each?
6. Whether the PP contain i. List of deliverables? ii. Project Objectives? iii. Due dates and intermediate milestones? iv. Plans like SQA Plan, Test Plan, Risk Management Plan etc.? vi. Tailoring / Deviation from Standard process (if any) vii. List of documents to be prepared? viii. Assumptions, Constraints & Risks
Requirements management | 1. Whether all the customer communications recorded?
2. Whether the minutes of meeting with customer recorded?
3. Has the SRS been reviewed and base lined
4. Does the SRS include use case diagram, use case specifications, user interface wireframes, non-functional requirements etc.?
5. Whether the customer acceptance criteria recorded in the SRS?
6. Whether the team keep a traceability matrix?
7. Whether the customer requirements traceable to SRS, SDD, Modules, Test cases and user manual?
8. Has the RTM been reviewed and base lined
9. Do the team changes the SRS and RTM when customer requirement changes? Does it under go CM control
Design | 1. Do the team prepare SDD document?
2. Does the SDD document include UML Diagrams, database designs and I/O designs?
3. Is it reviewed, approved and controlled?
Coding | 1. Check if code review is done
2. Check if unit testing done and Unit test cases are prepared
Testing | 1. Is there a test plan
2. Is the test environment specified
3. Are the test cases prepared and the test results recorded?
4. Does the test plan cover different levels of testing?
5. Are the Bug reports prepared and bugs assigned
Configuration Management | 1. Does the project plan identify SCIs?
2. Does the PP contain directory structure?
3. Does the QA member audit the CM activities?
4. Do they keep a list of project documents?
5. Do the SCIs base lined at each stage?
6. Do they undergo change control after baseline
7. Do all the documents have title, document issue status and amendment record?
8. How the SW is released? SW release note is prepared?
Intergroup coordination | 1. Are the inter dependencies of the project defined in the project plan?
2. Did the PM conduct a project kick off meeting to chalk out the action items for critical dependencies with other departments?
3. Do the project team review the team activities and intergroup coordination?
Risk management | 1. Does Project plan contain risk table?
2. Are the risks prioritized?
3. Is risk control mechanism planned?
Software Quality Assurance | 1. Does the QA Member involve at the project-planning phase?
2. Does the QA Member audit the project process?
3. Are the NCs cleared before passing to the next stage?
Corrective and Preventive Action | 1. Is the Corrective and Preventive Action report prepared for NCs?
2. Whether the cause analysis conducted for NCs?
3. Whether the Verification of effectiveness of Corrective and Preventive Action done?
4. Whether the follow-up of implementation of corrective and preventive action taken by QAD.
Project Closure | 1. Check if Metrics data collected, Poject peformance and Lessons learned are written down?
2. Whether the Project Closure Document is prepared and reviewed
3. Check if the project is closed
4. Check if Release note is given for test/client release

## HR
Review check list for HR Department
Processes to be verified | Check If / For
Management | 1. Whether HR goals in line with those of the organization
2. Whether workweeks identified and defined?
3. Whether full-time and part-time hours defined?
4. Check for Personal Details, Qualification and Experience Details of Employees
5. Check for organization chart
6. Check the status reporting process followed
Recruitment | 1. Do job descriptions exist for all jobs
2. Are job descriptions up to date
3. Check the Employee Application Form
4. Check if Aptitude/ technical test conducted
5. Check for Interview Assessment Form
6. How/When Background Checks are administered
7. Check for Offer letter, offer acceptance letter and Joining procedure
New Employee | 1. Are workplace policies communicated?
2. Whether the Employee Handbook up to date and accurate?
3. Has each employee received either the handbook or information on how to access the handbook on their own?
4. Do employee orientations take place?
Training | 1. Check for Training requisition form
2. Check for Training Attendance Sheet
3. Check if Training Feedback Form is Maintained
4. Check Training Effectiveness and Training Record
Confirmation/Annual Appraisal | 1. Verify Appraisal & Confirmation Procedure
2. Check for Appraisal process
Attendance/Leave | 1. Verify Muster Roll and Swipe Report
2. Check for Leave Request and Approval Procedure in Heads
Resignation Procedure | Check for Exit Interview and Clearance process
* Confidential records will not be verified in the internal audit procedure

## Testing
Review check list for ITT
Processes to be verified | Check If / For
Test Plan | Check if Test Plan is Prepared, reviewed and approved
1. Check if Test Case Document, Test Setup are Prepared and reviewed
Test Case | 2. Check if Traceability Matrix is updated with Test Case IDs
Test Execution | 1. Is the test environment (specified in Test Plan) made available for testing
2. Check if Traceability Matrix is updated with Test Case IDs
3. Are the Bug reports prepared and bugs assigned
4. Is regression testing done in subsequent iterations?
Task schedule | Is there a plan/task schedule for assignment of testers?