## Schedule & Effort Variance
Projects executed during 2017-18 - Schedule & Effort Variance
Project Code | Project Name | Estimated Effort | Start Date | Planned End Date | Actual End Date | Actual Effort | Schedule Variance | Effort Variance
P1 | Agile Scrum Tool Development Project | 276 | 2017-04-23 | 2017-08-10 | 2017-08-15 | 302 | 4.587% | 9.42%
P2 | Cworks CXF Project | 167 | 2017-05-01 | 2017-06-18 | 2017-06-26 | 220 | 16.67% | 31.74%
P3 | Leaflet Store Project | 58 | 2017-10-17 | 2017-11-15 | 2017-11-15 | 45 | 0% | -22.41%
P4 | ProjectScript | 560 | 2017-12-20 | 2018-04-20 | 2018-05-31 | 730 | 33.88% | 30.36%
P5 | Niko Hotels - Room Booking System | 120 | 2018-02-12 | 2018-03-31 | 2018-03-25 | 126 | -12.77% | 5%
Notes and Guidelines:
1 | The data given above are only sample data
2 | The texts in BLUE color are the data to be entered by the user
3 | Schedule variance and Effort Variance less than or equal to 0 are in Green background, greater than 0 but less than or equal to 5% are in Yellow background and greater than 5% are in Red background

## SPI & CPI
Schedule Performance Index (SPI) and Cost Performance Index (CPI)
Project Name: CWorks CXF Project
As on Date | 2018-06-14
Task ID | Task Name | Estimated Effort | Start Date | End Date | % Completion | PV | EV | AC | SPI | CPI
<TID1> | <Task Name 1> | 3 | 2018-06-03 | 2018-06-05 | 100% | 3 | 3 | 3.5 | 1 | 0.85714
<TID2> | <Task Name 2> | 5 | 2018-06-04 | 2018-06-08 | 90% | 5 | 4.5 | 4.5 | 0.9 | 1
<TID3> | <Task Name 3> | 9 | 2018-06-10 | 2018-06-18 | 45% | 6 | 4.05 | 4.15 | 0.675 | 0.9759
<TID4> | <Task Name 4> | 9 | 2018-06-12 | 2018-06-20 | 20% | 3.8571 | 1.8 | 1.75 | 0.46667 | 1.0286
<TID5> | <Task Name 5> | 1 | 2018-06-21 | 2018-06-21 | 0% | 0 | 0
<TID6> | <Task Name 6> | 3 | 2018-06-21 | 2018-06-23 | 0% | 0 | 0
<TID7> | <Task Name 7> | 7 | 2018-06-23 | 2018-06-29 | 0% | 0 | 0
<TID8> | <Task Name 8> | 1 | 2018-06-30 | 2018-06-30 | 0% | 0 | 0
<TID9> | <Task Name 9> | 5 | 31-06-2018 | 2018-07-04 | 0% | 0 | 0
<TID10> | <Task Name 10> | 4 | 2018-07-04 | 2018-07-07 | 0% | 0 | 0
<TID11> | <Task Name 11> | 1 | 2018-07-08 | 2018-07-08 | 0% | 0 | 0
<TID12> | <Task Name 12> | 1 | 2018-07-12 | 2018-07-12 | 0% | 0 | 0
[6 empty] | 17.8571 | 13.35 | 13.9 | 0.7476 | 0.96043
Notes and Guidelines:
1 | The data given above are only sample data
2 | The texts in BLUE color are the data to be entered by the user
3 | Estimated Effort (column C) can be in Person Days or Person Hours. Use the same unit of measure for all tasks consistently
4 | The Schedule Performance Index (SPI) and Cost Performance Index (CPI) are as on current date displayed in cell B3
5 | PV - Planned Value: Estimated effort (in Person Days or Person Hours, same unit as used for Estimated Effort) of tasks planned as on current date
6 | EV - Earned Value: Estimated effort (in Person Days or Person Hours, same unit as used for Estimated Effort) of tasks done as on current date
7 | AC - Actual Cost: Actual effort (in Person Days or Person Hours, same unit as used for Estimated Effort) of tasks done as on current date (taken from timesheet)
8 | SPI and CPI of less than 1 is BAD (behind schedule or cost overrun), greater than 1 is GOOD (ahead of schedule or within budget) and 1 is the ideal value
9 | SPI and CPI of less than 1 will be in Red background, greater than 1 will be in Green background and 1 will be in White background
Formulas:
PV = IF([Start Date]>B3,0,[Estimated Effort]*NETWORKDAYS([Start Date],IF(B3<[End Date],B3,[End Date]))/NETWORKDAYS([Start Date],[End Date]))

## QoW-Developers
Quality of Work (Based on Total Bugs) - Developers
Project Name: CWorks CXF Project
Sl. No. | Resource Name | Blocker & Critical Bugs |  | Major Bugs |  | Other Bugs |  | QoW
1 | <Developer 1> | 1 | 0.075 | 4 | 0.032432 | 9 | 0.013235 | 87.93%
2 | <Developer 2> | 1 | 0.075 | 9 | 0.072973 | 26 | 0.038235 | 81.38%
3 | <Developer 3> | 2 | 0.15 | 8 | 0.064865 | 13 | 0.019118 | 76.6%
4 | <Developer 4> | 4 | 0.3 | 13 | 0.10541 | 16 | 0.023529 | 57.11%
5 | <Developer 5> |  | 0 | 3 | 0.024324 | 4 | 0.0058824 | 96.98%
SCORING GUIDELINES
Column | FACTORS | DESCRIPTION
C | Blocker & Critical Bugs | No. of blocker & critical bugs in the code written by the developer
E | Major Bugs | No. of major bugs in the code written by the developer
G | Other Bugs | No. of normal, minor & trivial bugs in the code written by the developer
I | Quality of Work | 100 - (weighted % of bugs created by the developer; critical - 60% weightage; major - 30% weightage; minor - 10% weightage)
Assumptions and Limitations
1 | Origin or source of bugs could be RS or Design in which case developer of the program is not the responsible person for bug
2 | Critical bugs are given 60% weightage; major bugs - 30% and minor bugs - 10% weightage in calculating the quality of work; Can be changed in the formula as required.
3 | Number of bugs in a complex screen may be more compared to a low complex screen. So, complexity factor should also be considered while calculating Quality of Work score (To be discussed further and decide how to take care this)

## QoW-Testers
Quality of Work (Based on Total Bugs) - Testers
Project Name: CWorks CXF Project
Sl. No. | Resource Name | Blocker & Critical Bugs |  | Major Bugs |  | Other Bugs |  | QoW
1 | <Tester 1> | 1 | 0.075 | 4 | 0.032432 | 9 | 0.013235 | 12.07%
2 | <Tester 2> | 1 | 0.075 | 9 | 0.072973 | 26 | 0.038235 | 18.62%
3 | <Tester 3> | 2 | 0.15 | 8 | 0.064865 | 13 | 0.019118 | 23.4%
4 | <Tester 4> | 4 | 0.3 | 13 | 0.10541 | 16 | 0.023529 | 42.89%
5 | <Tester 5> |  | 0 | 3 | 0.024324 | 4 | 0.0058824 | 3.021%
SCORING GUIDELINES
Column | FACTORS | DESCRIPTION
C | Blocker & Critical Bugs | No. of blocker & critical bugs detected by the tester
E | Major Bugs | No. of major bugs detected by the tester
G | Other Bugs | No. of normal, minor & trivial bugs detected by the tester
I | Quality of Work | Weighted % of bugs detected by the tester (critical - 60% weightage; major - 30% weightage; minor - 10% weightage)
Assumptions and Limitations
1 | Critical bugs are given 60% weightage; major bugs - 30% and minor bugs - 10% weightage in calculating the quality of work; Can be changed in the formula as required.
2 | Number of bugs in a complex module may be more compared to a low complex module. So, number of bugs detected by a tester will also depend on the module assigned to the tester for testing (To be discussed further and decide how to take care this).

## Bug Density-Modules
Bug Density - Module-wise
Project Name: CWorks CXF Project
Sl. No. | Module Name | Blocker & Critical Bugs |  | Major Bugs |  | Other Bugs |  | Bug Density
1 | <Module 1> | 1 | 0.075 | 4 | 0.032432 | 9 | 0.013235 | 12.07%
2 | <Module 2> | 1 | 0.075 | 9 | 0.072973 | 26 | 0.038235 | 18.62%
3 | <Module 3> | 2 | 0.15 | 8 | 0.064865 | 13 | 0.019118 | 23.4%
4 | <Module 4> | 4 | 0.3 | 13 | 0.10541 | 16 | 0.023529 | 42.89%
5 | <Module 5> |  | 0 | 3 | 0.024324 | 4 | 0.0058824 | 3.021%
SCORING GUIDELINES
Column | FACTORS | DESCRIPTION
C | Blocker & Critical Bugs | No. of blocker & critical bugs detected in the module
E | Major Bugs | No. of major bugs detected in the module
G | Other Bugs | No. of normal, minor & trivial bugs detected in the module
I | Bug Density | % of weighted sum of bugs detected in the module (critical - 60% weightage; major - 30% weightage; minor - 10% weightage)
Assumptions and Limitations
1 | Critical bugs are given 60% weightage; major bugs - 30% and minor bugs - 10% weightage in calculating the quality of work; Can be changed in the formula as required.
3 | Number of bugs in a complex module may be more compared to a low complex modules.

## Bugs-Aging
Bugs - Aging (How long a bug has been kept Open before fixing/closing)
Project Name: CWorks CXF Project
Sl. No. | Bug ID | Bug Description | Date Bug Reported | Date Bug Closed | Days Bug Remained Open
1 | <Bug ID 1> | <Bug Description 1> | 2017-08-10 | 2017-08-15 | 4
2 | <Bug ID 2> | <Bug Description 2> | 2017-06-18 | 2017-06-26 | 6
3 | <Bug ID 3> | <Bug Description 3> | 2017-11-15 | 2017-11-15 | 1
4 | <Bug ID 4> | <Bug Description 4> | 2018-04-20 | 2018-05-31 | 30
5 | <Bug ID 5> | <Bug Description 5> | 2018-03-31 | 2018-03-31 | 0
Formulas:
Days Bug Remained Open = NETWORKDAYS([Date Bug Reported],[Date Bug Closed])

## Requirement Stability Index
Projects executed during 2017-18 - Requirement Stability Index (RSI)
Project Name: CWorks CXF Project
Project Code | Project Name | Total No. of Original Requirements | New Requirements added after SRS Baselining | Requirements changed after SRS Baselining | Requirement Stability Index (RSI)
P1 | Agile Scrum Tool Development Project | 65 | 5 | 6 | 83.08%
P2 | Cworks CXF Project | 12 | 1 | 2 | 75%
P3 | Leaflet Store Project | 10 | 1 | 1 | 80%
P4 | ProjectScript | 209 | 24 | 56 | 61.72%
P5 | Niko Hotels - Room Booking System | 36 | 4 | 12 | 55.56%
Notes and Guidelines:
1 | The data given above are only sample data
2 | The texts in BLUE color are the data to be entered by the user
3 | Requirement Stability Index of 100% indicates that requirements were stable and there were no changes. Lower values indicates instability of requirements and more changes in requirements